## Total Tickets
Number | Created | Short description | Category | Type | State | Business Service | Assignment group | Assigned to | Change Initiator | Country
CHG175833 | 2017-06-02 15:58 | Outound Internet from DMZ to ANY blocked | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG175954 | 2017-06-05 12:17 | KD Plaza: WAN Link configuration and IPSec VPN on Tikona Internet Link | Infrastructure | Emergency | Closed | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG176190 | 2017-06-06 19:18 | ERP RES\RAMP: Extension of SQL Jobs history retention | Infrastructure | Normal | In progress | IN ERP - RES | IN PROD Data Center | Dinakar Naidu | C1.NIIT Saimani | India
CHG176237 | 2017-06-07 09:12 | Network Device password change due to release of one resource | Infrastructure | Emergency | Closed | IN DC Network | IN PROD Service Transition |  | C1.NIIT Kamal | India
CHG176309 | 2017-06-07 14:39 | HR Induction Project | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG176681 | 2017-06-09 13:53 | HR Induction Project | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG177116 | 2017-06-14 07:28 | Jharsuguda: Implementation of VodaFone MPLS Link | Infrastructure | Normal | Closed | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177117 | 2017-06-14 07:46 | Hazra, Kolkata:Implementation of VodaFone MPLS Link | Infrastructure | Normal | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177151 | 2017-06-14 10:45 | Centrium, Gurgaon: Implementation of VodaFone MPLS Link | Infrastructure | Normal | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177288 | 2017-06-15 09:36 | June -2017: Deployment of latest Microsoft monthly patches in the UAT ENV | Infrastructure | Normal | In progress | IN Microsoft/other Software | IN PROD Data Center | C1.NIIT Bhupendra | C1.NIIT Bhupendra | India
CHG178169 | 2017-06-21 18:10 | CRM 4.0 to CRM 2016 Cloud - Microsoft Dynamics 365 ¦ Transition from On Premise to Cloud solution | Application | Normal | Closed | IN Microsoft Dynamics | IN SDM Central Services | Raviprasanth Gopal | Raviprasanth Gopal | India
CHG178296 | 2017-06-22 14:18 | Hirecraft - Vulnerability Assessment - Fix | Application | Normal | In progress | IN Hirecraft | IN PROD GCC Service desk | Mahantesh Hiremath | Saritha Mc | India
CHG178396 | 2017-06-23 07:40 | REST API For Career Site Integration | Application | Normal | In progress | IN Hirecraft | IN SDM Candidate | Nizamuddin A | Nizamuddin A | India
CHG178397 | 2017-06-23 07:59 | RIM 10.2: Review of Generic/Service accounts with Password | Application | Normal | Closed | IN AMS | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG178454 | 2017-06-23 13:04 | CRM 4.0 to CRM 2016 Cloud - Microsoft Dynamics 365 ¦ Transition from On Premise to Cloud solution | Application | Normal | In progress | IN Microsoft Dynamics | IN SDM Central Services | Raviprasanth Gopal | Raviprasanth Gopal | India
CHG178453 | 2017-06-23 13:29 | RIM compliance Tracking Tool | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Dharmanna Undri | Dharmanna Undri | India
CHG178472 | 2017-06-23 14:30 | RIM 10.2: Review of Generic/Service accounts with Password | Application | Normal | In progress | IN AMS | IN PROD Data Center | Mahantesh Hiremath | Prabhu Kgs | India
CHG178771 | 2017-06-27 06:29 | Addition of new Azure Adecco France IP to TCS S2S VPN | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG179135 | 2017-06-29 06:20 | IP addition for TCS IPSec VPN site to site on Adecco DC firewall | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG179312 | 2017-06-30 07:22 | Black list IP on DC Firewall | Infrastructure | Emergency | New | IN DC Network | IN PROD Service Transition |  | C1.NIIT Kamal | India
CHG179372 | 2017-06-30 12:30 | Replacing existing WSUS\LUP server hardware with new Dell PE R710. | Application | Normal | In progress | IN Microsoft/other Software | IN PROD Data Center | Mahantesh Hiremath | Mahantesh Hiremath | India

## Infra
Number | Created | Short description | Category | Type | State | Business Service | Assignment group | Assigned to | Change Initiator | Country
CHG175833 | 2017-06-02 15:58 | Outound Internet from DMZ to ANY blocked | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG175954 | 2017-06-05 12:17 | KD Plaza: WAN Link configuration and IPSec VPN on Tikona Internet Link | Infrastructure | Emergency | Closed | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG176190 | 2017-06-06 19:18 | ERP RES\RAMP: Extension of SQL Jobs history retention | Infrastructure | Normal | In progress | IN ERP - RES | IN PROD Data Center | Dinakar Naidu | C1.NIIT Saimani | India
CHG176237 | 2017-06-07 09:12 | Network Device password change due to release of one resource | Infrastructure | Emergency | Closed | IN DC Network | IN PROD Service Transition |  | C1.NIIT Kamal | India
CHG177116 | 2017-06-14 07:28 | Jharsuguda: Implementation of VodaFone MPLS Link | Infrastructure | Normal | Closed | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177117 | 2017-06-14 07:46 | Hazra, Kolkata:Implementation of VodaFone MPLS Link | Infrastructure | Normal | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177151 | 2017-06-14 10:45 | Centrium, Gurgaon: Implementation of VodaFone MPLS Link | Infrastructure | Normal | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG177288 | 2017-06-15 09:36 | June -2017: Deployment of latest Microsoft monthly patches in the UAT ENV | Infrastructure | Normal | In progress | IN Microsoft/other Software | IN PROD Data Center | C1.NIIT Bhupendra | C1.NIIT Bhupendra | India
CHG178771 | 2017-06-27 06:29 | Addition of new Azure Adecco France IP to TCS S2S VPN | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG179135 | 2017-06-29 06:20 | IP addition for TCS IPSec VPN site to site on Adecco DC firewall | Infrastructure | Emergency | In progress | IN DC Network | IN PROD Network | C1.NIIT Kamal | C1.NIIT Kamal | India
CHG179312 | 2017-06-30 07:22 | Black list IP on DC Firewall | Infrastructure | Emergency | New | IN DC Network | IN PROD Service Transition |  | C1.NIIT Kamal | India

## Application
Number | Created | Short description | Category | Type | State | Business Service | Assignment group | Assigned to | Change Initiator | Country
CHG176309 | 2017-06-07 14:39 | HR Induction Project | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG176681 | 2017-06-09 13:53 | HR Induction Project | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG178169 | 2017-06-21 18:10 | CRM 4.0 to CRM 2016 Cloud - Microsoft Dynamics 365 ¦ Transition from On Premise to Cloud solution | Application | Normal | Closed | IN Microsoft Dynamics | IN SDM Central Services | Raviprasanth Gopal | Raviprasanth Gopal | India
CHG178296 | 2017-06-22 14:18 | Hirecraft - Vulnerability Assessment - Fix | Application | Normal | In progress | IN Hirecraft | IN PROD GCC Service desk | Mahantesh Hiremath | Saritha Mc | India
CHG178396 | 2017-06-23 07:40 | REST API For Career Site Integration | Application | Normal | In progress | IN Hirecraft | IN SDM Candidate | Nizamuddin A | Nizamuddin A | India
CHG178397 | 2017-06-23 07:59 | RIM 10.2: Review of Generic/Service accounts with Password | Application | Normal | Closed | IN AMS | IN SDM Middle Office – AMS | Prabhu Kgs | Prabhu Kgs | India
CHG178454 | 2017-06-23 13:04 | CRM 4.0 to CRM 2016 Cloud - Microsoft Dynamics 365 ¦ Transition from On Premise to Cloud solution | Application | Normal | In progress | IN Microsoft Dynamics | IN SDM Central Services | Raviprasanth Gopal | Raviprasanth Gopal | India
CHG178453 | 2017-06-23 13:29 | RIM compliance Tracking Tool | Application | Normal | Closed | IN Microsoft/other Software | IN SDM Middle Office – AMS | Dharmanna Undri | Dharmanna Undri | India
CHG178472 | 2017-06-23 14:30 | RIM 10.2: Review of Generic/Service accounts with Password | Application | Normal | In progress | IN AMS | IN PROD Data Center | Mahantesh Hiremath | Prabhu Kgs | India
CHG179372 | 2017-06-30 12:30 | Replacing existing WSUS\LUP server hardware with new Dell PE R710. | Application | Normal | In progress | IN Microsoft/other Software | IN PROD Data Center | Mahantesh Hiremath | Mahantesh Hiremath | India

## Dashboard
Change Ticket Dash Board
Category |  |  | State
Category | Business Service | Assignment group | Closed | In progress | Grand Total
Application | IN AMS | IN SDM Middle Office – AMS | 1 | 0 | 1
| IN ERP - RES/RAMP | IN PROD Data Centre | 0 | 0 | 0
|  | IN SDM Central Services | 0 | 0 | 0
| IN Microsoft/other Software | IN SDM Middle Office – AMS | 3 | 0 | 3
| IN Hirecraft | IN SDM Candidate | 0 | 1 | 1
Application Total |  |  |  |  | 5
Infrastructure | IN DC Network | IN PROD Network | 2 | 5 | 7
| IN Microsoft/other Software | IN PROD Data Center / IN PROD Service Transition | 0 | 1 | 1
| IN DC Network |  | 0 | 0 | 0
| IN Access Management |  | 0 | 0 | 0
Infrastructure Total |  |  |  |  | 8
Grand Total |  |  |  |  | 13